# Project Meeting Minutes

Date of meeting(s): **17-Feb-2023 (week 6)**

Group Number: **Group 11 (Section 4)**

Group members present (Name, ID):

* Deep Johal - 0787880
* Mahesh Bhanudas Gujarathi - 0791269
* Rugveda Rajendra Shirgaonkar - 0780896
* Kavya Vijay - 0789148
* Julie Kunnuvila Thomas - 0792998

Specific Activities that were completed/worked on:

|  |  |
| --- | --- |
| **Activity** | **Activity Owner** |
| Found dataset to cover the complete Canadian Long Term Housing Market | Kavya, Julie |
| Started initial data cleaning and analysis on the main dataset | Rugveda, Mahesh, Deep |
| Discussed about the work distribution | Team |
| Attended Interview | Team |

Specific Output from work:

* Finalized the one dataset.
* Documented the project plan and data assessment.
* Discussed final project goal with project coordinator.

On Target:

* Indicate the current status of your project:
  + \_\_\_\_\_ green: everything on track for completion by due date
  + \_\_\_\_\_ yellow: a small number of tasks are off track and completion by due date is at risk
  + \_\_\_\_\_ red: many tasks are off track and project will not be completed by due date

Challenges/Disagreements:

* **The data set we got has lot of information, that is not required for our project. Hence, it is taking more time that we expected to clean and go forward with further analysis.**

Planned Activities for coming week:

* List brief description of activities,

Julie, Kavya

* + - Planning to do Ontario age wise analysis and some visualization to get an insight about the overall age distribution and the number of senior citizens.

Rugveda , Mahesh

* cleaning data since the start as the dataset we have is for the whole Ontario and for now we are focusing on only senior housing needed for western Ontario in such. Working on preprocessing focusing on data Quality assessment where we are handling missing values in the data.

Deep

* Looking for more data online that might give us a clear picture about the income of the senior citizens and their requirements from these senior homes. Also looking data related to other services like rehabs, hospitals and how having more senior homes might help the regional hospitals handling their patients . Also working on data cleaning of the existing dataset.

Team

* Preparing for mid-term presentation